## Sheet1
H.V.E.C Dashboard Project Cost Estimate
Prepared by: HVEC PMO | Date: | 2024-01-05
Note: Change the WBS items and other entries to meet your project needs. This data is from Figure 7-1 of Schwalbe's text
Information Technology Project Management, Fourth Edition. Also make sure the formulas work properly based on the data you enter.
| # Units/Hrs. | Cost/Unit/Hr. | Subtotals | WBS Level 1 Totals | % of Total
WBS Items
1. Devolper Team |  |  |  | 17006 | 21.19%
1.1 Program Devloper | 720 | 23.62 | 17006.4
2. Business Analyst Team |  |  |  | 24718 | 30.8%
2.1 Business Analyst | 680 | 36.35 | 24718
3. Data Analyst Team |  |  |  | 10291.2 | 12.82%
3.1 Data Analyst | 320 | 32.16 | 10291.2
4. Marketing |  |  |  | 28233.6 | 35.18%
4.1 System Testing | 680 | 41.52 | 28233.6
Total project cost estimate |  |  |  | 80248.8
* See software development estimate

## Sheet2
* Software development
Contractor labor estimate | 3000 | 150 | 450000
Project team member estimate | 1920 | 75 | 144000
Total labor estimate |  |  | 594000
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 10 | 4 | 40
External interface files | 3 | 7 | 21
External outputs | 3 | 5 | 15
External queries | 3 | 4 | 12
Logical internal tables | 6 | 10 | 60
Total function points |  |  | 148
Java 2 languange equivalency value |  |  | 46
Source lines of code (SLOC) estimate |  |  | 6808
Productivity *KSLOC^Penalty (person months) | 30.2659
Total labor hours (160 hours/month) | 4842.5507
Cost/labor hour ($120/hour) | 120
Total software development estimate | 581106.0898