## Sheet1
| Project Name: | High Voltage Energy Company Dashboard | Project Manager: | Chandi G, Melvin P, Kyle S, Vicente A-L
| Updated By: | HVEC PMO | Date : | 2024-01-08
| Scope of Project: | High Voltage’s development team will create and implement a data analytics dashboard that provides actionable insights into customer behavior and market trends.
| Product Justicfication: | The analytic dash board will be a smooth user-friendly interface system allows easy to access and the ability to read field measurements, weather forecasting, and predicative analytics. The dash board will also feature security, and access control along with revenue and production cost.
# | Description of product or service | Date of request | Requested by: | Department | Procurement method selected | Action Date | Delievery date | Status
1 | Gather requirements from stakeholders to understand their needs and expectations | 2023-01-04 | PM Team | IT, Makreting, Product Development | Internal Source | 2024-01-04 | 2024-01-25 | Delivered
2 | Data Assessment and Preparation | 2023-01-05 | PM Team | Data Aanlytics | Internal Source | 2024-01-05 | 2024-02-08 | In process
3 | Design and Prototyping | 2023-01-04 | PM Team | Marketing and Product Development | Internal Source | 2024-01-04 | 2024-02-22 | In Process
4 | Dashboard Development | 2023-01-04 | PM Team | IT | Internal Source | 2024-01-04 | 2024-02-22 | Pending
5 | Testing | 2024-05-26 | PM Team | Marketing and Product Development | Internal Source | 2024-06-26 | 2024-08-04 | Pending
6 | Training & Materials | 2024-05-26 | PM Team | Product Deveopement | Small Purchase | 2024-06-26 | 2024-08-04 | Pending
7 | Deployment | 2023-01-04 | PM Team | IT | Internal Source | 2024-07-18 | 2023-08-04 | Pending