## Sheet1
Risk Register for #4
Prepared by: |  | HVEC PMO |  |  | Date: 01/11/2024
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
1 | 1 | Data Security and Privacy Breach | Unauthorized access or data breaches leading to the compromise of sensitive information. | Information Security | Weak authentication, lack of encryption, or vulnerabilities in the system. | External hacking attempts, internal security lapses. | Implement strong encryption, multi-factor authentication, regular security audits, and employee training. |  | High | High
2 | 2 | Data Accuracy and Quality Issues | Inaccurate or poor-quality data affecting the reliability of analytics and decision-making. | Data Management | Data entry errors, lack of data validation processes. | Inconsistent data sources, manual data input errors. | Establish data quality standards, implement validation checks, and provide user training. |  | Medium | High
3 | 3 | System Downtime | Technical issues or system failures leading to downtime and disrupting decision-making processes. | Operational | Infrastructure issues, software bugs, lack of redundancy. | Hardware failure, software glitches, cyberattacks. | Robust IT infrastructure, regular maintenance, contingency planning. |  | High | High
4 | 7 | Insufficient User Training | Inadequate training leading to misinterpretation of data and improper dashboard usage. | Human Factor | Lack of training programs, outdated training materials. | New dashboard features, updates. | Comprehensive user training, regular updates to training materials. |  | Medium | Medium
5 | 8 | Lack of User Adoption | Resistance among users leading to underutilization of the dashboard. | Human Factor | Poor communication, unaddressed user concerns. | Introduction of the dashboard, changes in business processes. | User involvement in design, addressing concerns, ongoing support, and feedback. |  | Medium | Medium
6 | 4 | Integration Challenges | Difficulty integrating the dashboard with existing systems and databases. | Technical | Incompatible technologies, lack of expertise. | System upgrades, changes in data sources. | Thorough compatibility assessments, involving IT professionals. |  | Medium | High
7 | 5 | Scalability Issues | Inability to scale the dashboard to handle increasing data volumes and user demands. | Technical | Lack of scalability planning, outdated technology. | Increase in data volume, growth of user base. | Scalable infrastructure, regular performance assessments. |  | High | High
8 | 6 | Ethical Considerations | Ethical concerns related to biased decision-making or misuse of data. | Ethical | Lack of ethical guidelines, biased algorithms. | Implementation of new analytics models, changes in data sources. | Establish and enforce ethical guidelines, incorporate bias detection mechanisms. |  | Medium | Medium