## HVEC_Internal_Dashboard (1)
Task ID | Created At | Completed At | Last Modified | Name | Section/Column | Assignee | Assignee Email | Start Date | Due Date
1206289429069610 | 2024-01-05 |  | 2024-01-05 | Clearly define the objectives of the dashboard. | Define Objectives and Requirements |  |  | 2024-01-15 | 2024-01-28
1206289429069620 | 2024-01-05 |  | 2024-01-05 | Gather requirements from stakeholders to understand their needs and expectations. | Define Objectives and Requirements |  |  | 2024-01-29 | 2024-02-11
1206289429069620 | 2024-01-05 |  | 2024-01-05 | Evaluate existing data sources and assess data quality. | Data Assessment and Preparation |  |  | 2024-02-12 | 2024-02-25
1206289429069620 | 2024-01-05 |  | 2024-01-05 | Prepare and clean the data for integration into the dashboard. | Data Assessment and Preparation |  |  | 2024-02-26 | 2024-03-10
1206289429069620 | 2024-01-05 |  | 2024-01-05 | Create wireframes and prototypes to visualize the dashboard layout and features. | Design and Prototyping |  |  | 2024-03-11 | 2024-03-31
1206289429069630 | 2024-01-05 |  | 2024-01-05 | Gather feedback from stakeholders and make necessary adjustments. | Design and Prototyping |  |  | 2024-04-01 | 2024-04-21
1206289429069630 | 2024-01-05 |  | 2024-01-05 | Develop the backend infrastructure for data storage and processing. | Development |  |  | 2024-04-22 | 2024-05-05
1206289429069630 | 2024-01-05 |  | 2024-01-05 | Implement frontend components for the user interface. | Development |  |  | 2024-05-06 | 2024-05-26
1206289429069630 | 2024-01-05 |  | 2024-01-05 | Integrate with external systems and APIs as needed. | Development |  |  | 2024-05-27 | 2024-06-16
1206289429069640 | 2024-01-05 |  | 2024-01-05 | Conduct thorough testing to identify and fix any bugs or issues. | Testing |  |  | 2024-06-17 | 2024-07-07
1206289429069640 | 2024-01-05 |  | 2024-01-05 | Perform user acceptance testing (UAT) with stakeholders to ensure the dashboard meets requirements. | Testing |  |  | 2024-07-08 | 2024-07-28
1206289429069640 | 2024-01-05 |  | 2024-01-05 | Roll out the dashboard to a limited audience for initial feedback. | Deployment |  |  | 2024-07-29 | 2024-08-11
1206289429069640 | 2024-01-05 |  | 2024-01-05 | Address any issues that arise during the deployment phase. | Deployment |  |  | 2024-08-12 | 2024-08-25
1206289429069650 | 2024-01-05 |  | 2024-01-05 | Develop training materials for end-users and administrators. | Training and Documentation |  |  | 2024-08-26 | 2024-09-08
1206289429069650 | 2024-01-05 |  | 2024-01-05 | Conduct training sessions and provide ongoing support. | Training and Documentation |  |  | 2024-09-09 | 2024-09-22